## whole-app-uat-test-cases
Test ID | Area | Module | Role | Priority | Preconditions | Scenario | Steps | Expected Result | Status | Owner | Notes
UAT-001 | Authentication | Login | All | H | Application deployed; seeded users exist; tester knows valid credentials | Login with valid credentials | 1. Open login page; 2. Enter valid username and password; 3. Submit form | User is authenticated and lands on SME Academy without errors; top navigation renders for authenticated user | Not Started
UAT-002 | Authentication | Login | All | H | Application deployed | Reject invalid credentials | 1. Open login page; 2. Enter invalid username or password; 3. Submit form | Login is rejected with a clear validation message and user remains unauthenticated | Not Started
UAT-003 | Authentication | Logout | All | H | User is logged in | Logout from the application | 1. Click sign out; 2. Confirm request if prompted | Session ends and user returns to the login page; protected pages require login again | Not Started
UAT-004 | Authentication | Password Reset | All | M | Email backend configured for environment | Request password reset | 1. Open forgot password flow; 2. Enter known email address; 3. Submit request | Password reset confirmation appears and email dispatch is recorded according to environment settings | Not Started
UAT-005 | Navigation | Suite Dashboard | CEO | H | CEO test user exists and can log in | View the business modules dashboard | 1. Log in as CEO; 2. Open root dashboard | Dashboard shows grouped modules, help text popovers, available links, and business summary widgets | Not Started
UAT-006 | Navigation | Role-Based Navigation | Staff | H | Staff test user exists and can log in | Verify restricted module visibility for standard staff | 1. Log in as staff user; 2. Open dashboard; 3. Review visible module tiles | Staff user sees permitted modules only and does not see payroll or system admin if not authorized | Not Started
UAT-007 | Navigation | Return Navigation | All | M | User is logged in and on a module page | Return from a module page to dashboard | 1. Open any module except dashboard; 2. Use back-to-dashboard navigation | User is taken back to dashboard and navigation remains consistent | Not Started
UAT-008 | Navigation | Academy Tools Links | All | M | User can open original prototype academy page if used in UAT scope | Open Business Tools links from prototype tools section | 1. Open prototype academy tools section; 2. Click each tool card link | Each tool card opens the mapped live Django page without broken links | Not Started
UAT-009 | CRM | Clients | H | At least one authenticated business user exists | Create a client record | 1. Open CRM and customers module; 2. Create a new client with required data; 3. Save | Client is created, visible in client list, and searchable | Not Started
UAT-010 | CRM | Clients | M | At least one client exists | Edit a client record | 1. Open an existing client; 2. Change contact or profile details; 3. Save | Updated client details persist and appear in list/detail views | Not Started
UAT-011 | CRM | Clients | M | Multiple clients exist | Filter or search clients | 1. Open client register; 2. Use search and any filter controls | Results narrow correctly and clear actions restore the full list | Not Started
UAT-012 | CRM | Engagements | H | At least one client exists | Create an engagement for a client | 1. Open engagements; 2. Create a new engagement linked to a client; 3. Save | Engagement is created with assigned owner and visible in register/detail views | Not Started
UAT-013 | CRM | Engagements | M | At least one engagement exists | Advance or update engagement details | 1. Open an engagement; 2. Update status, owner, or dates; 3. Save | Changes persist and engagement reporting reflects the update | Not Started
UAT-014 | Sales | Sales Orders | H | At least one client and one product/service exist | Create a sales order | 1. Open sales orders; 2. Create order for a customer; 3. Add items and totals; 4. Save | Sales order is created and appears in order list with correct total | Not Started
UAT-015 | Sales | Sales Orders | H | At least one draft sales order exists | Confirm and fulfil a sales order | 1. Open draft sales order; 2. Confirm order; 3. Fulfil stock or service delivery step | Status changes correctly and downstream invoicing becomes available when appropriate | Not Started
UAT-016 | Finance | Invoicing & Billing | H | At least one client and billable item exist | Create a customer invoice | 1. Open billing; 2. Create invoice; 3. Add line items; 4. Save | Invoice is created with correct amounts, tax, and customer association | Not Started
UAT-017 | Finance | Invoicing & Billing | H | At least one issued invoice exists | Record customer payment | 1. Open issued invoice; 2. Capture full or partial payment; 3. Save | Invoice balance updates correctly and payment history is recorded | Not Started
UAT-018 | Finance | Expense Tracking | H | Expense categories and an authenticated approver exist | Submit a business expense | 1. Open expenses; 2. Create expense with amount and category; 3. Submit | Expense enters approval workflow with correct status and audit trail | Not Started
UAT-019 | Finance | Expense Tracking | H | Submitted expense exists and approver is authorized | Approve or reject an expense | 1. Log in as approver; 2. Open submitted expense; 3. Approve or reject | Decision is stored, status changes correctly, and the submitter can see the result | Not Started
UAT-020 | Finance | Financial Overview | H | Baseline finance, billing, and expense records exist | Review financial overview | 1. Open financial overview module; 2. Compare headline values to source transactions | Revenue, expenses, profit, and pipeline values reflect underlying records consistently | Not Started
UAT-021 | Finance | Accounting | H | Chart of accounts exists | Create a journal entry | 1. Open accounting module; 2. Create journal entry with balanced debit and credit lines; 3. Save or post | Balanced journal entry is accepted and appears in ledger according to status | Not Started
UAT-022 | Finance | Accounting | H | Bank-related accounts exist; sample statement file available | Import bank statement | 1. Open bank statement import flow; 2. Upload supported file; 3. Complete import | Statement lines import successfully and are available for reconciliation | Not Started
UAT-023 | Finance | Accounting | H | Imported bank statement lines and matching journal activity exist | Reconcile bank activity | 1. Open reconciliation view; 2. Match one or more lines; 3. Save reconciliation | Matched items are marked reconciled and unmatched items remain visible for later review | Not Started
UAT-024 | Finance | Payroll | H | Authorized payroll user exists; employee records exist | Open payroll as authorized user | 1. Log in as admin or CEO; 2. Open payroll module | Payroll page loads and restricted payroll information is visible only to authorized users | Not Started
UAT-025 | Finance | Payroll | H | Unauthorized standard user exists | Block payroll access for unauthorized user | 1. Log in as non-authorized staff; 2. Attempt to open payroll route | User is denied access or redirected according to access policy | Not Started
UAT-026 | Operations | Products & Services | H | Authenticated business user exists | Create a product or service | 1. Open products and services; 2. Add a new item with price and required fields; 3. Save | Item is created, listed, and available for downstream sales or purchasing flows | Not Started
UAT-027 | Operations | Products & Services | M | At least one product exists | Edit pricing or attributes for a product | 1. Open existing item; 2. Change price, type, or metadata; 3. Save | Changes persist and are reflected in subsequent transactional forms | Not Started
UAT-028 | Operations | Inventory | H | Inventory locations and at least one stock item exist | Capture stock movement | 1. Open inventory; 2. Record inbound, outbound, or adjustment movement; 3. Save | Stock quantity updates correctly and movement history is recorded | Not Started
UAT-029 | Operations | Inventory | H | Low-stock thresholds configured on at least one item | Trigger or review low stock status | 1. Reduce stock below threshold or open a known low-stock item; 2. Refresh inventory views | Low-stock indicator appears consistently in inventory and related reporting | Not Started
UAT-030 | Operations | Purchasing | H | Supplier and catalogue item exist | Create a purchase order | 1. Open purchasing; 2. Create PO for supplier; 3. Add items and quantities; 4. Save | Purchase order is created and visible with correct supplier and totals | Not Started
UAT-031 | Operations | Purchasing | H | Approved purchase order exists | Receive goods against purchase order | 1. Open approved PO; 2. Record receipt; 3. Save | Inventory levels increase appropriately and PO status updates to part/fully received | Not Started
UAT-032 | Operations | Tasks & Kanban | M | Authenticated user exists | Create a task on the board | 1. Open tasks; 2. Add a board or use existing board; 3. Create task; 4. Save | Task appears in the correct column with title, assignee, and metadata | Not Started
UAT-033 | Operations | Tasks & Kanban | M | At least one task exists | Move task between workflow stages | 1. Open board; 2. Drag or update task to new stage | Task moves successfully and updated state persists after reload | Not Started
UAT-034 | Operations | Documents | H | Authenticated user exists; sample file available | Upload a document | 1. Open documents library; 2. Upload supported file; 3. Save metadata if required | Document uploads successfully and appears in library with accessible link/version | Not Started
UAT-035 | Operations | Documents | M | Uploaded document exists | Download or preview an uploaded document | 1. Open document record; 2. Download or preview file | Correct file is returned and metadata/version remains intact | Not Started
UAT-036 | Insights | Reports & Analytics | H | Representative data exists across modules | Open analytics dashboard | 1. Open reports and analytics; 2. Review charts and tables | Charts load without errors and reflect current transactional data | Not Started
UAT-037 | Insights | Reports & Analytics | M | Representative data exists | Filter analytics results | 1. Apply date or module filters; 2. Compare visible results | Filtered results update correctly and clear/reset returns baseline report state | Not Started
UAT-038 | Insights | Alerts | H | Alert-producing conditions exist or pipeline can be run | Review active alerts | 1. Open alerts list; 2. Review statuses and details | Relevant alerts display clearly with accurate status and affected record context | Not Started
UAT-039 | Insights | Alerts | M | At least one open alert exists | Resolve an alert | 1. Open alert detail or action control; 2. Mark as resolved | Alert status changes to resolved and it no longer appears in active alert list | Not Started
UAT-040 | Insights | Comms Health | M | Clients and communication data exist | Review communication health | 1. Open communication health; 2. Review summary and at-risk relationships | Communication coverage and at-risk indicators load correctly from source contact data | Not Started
UAT-041 | Insights | Communication Log | M | At least one client exists | Log a communication interaction | 1. Open log contact flow; 2. Enter contact details; 3. Save | Interaction is recorded and contributes to relationship history or health scoring | Not Started
UAT-042 | Insights | AI Insights | M | Baseline transactional data exists | Open AI insights module | 1. Open AI insights; 2. Review forecast and readiness sections | Insights page loads, summary cards render, and no calculation panel throws an error | Not Started
UAT-043 | Insights | AI Insights | M | Authorized user can trigger insight refresh if supported | Run available AI/rule-based alert pipeline | 1. Trigger available insight or alert action; 2. Wait for completion | Action completes with visible confirmation and updated output where applicable | Not Started
UAT-044 | People | Staff | H | Authorized user exists | Create a staff record | 1. Open staff directory; 2. Add a staff member; 3. Save | Staff record is created and visible in the directory | Not Started
UAT-045 | People | Staff | M | At least one staff member exists | Edit or deactivate a staff member | 1. Open a staff detail or action; 2. Update or deactivate; 3. Save | Changes persist and active/inactive state behaves as expected in listings | Not Started
UAT-046 | People | Departments | H | Authorized user exists | Create or edit a department | 1. Open departments; 2. Create or update department data; 3. Save | Department persists and becomes selectable in related staff or work records | Not Started
UAT-047 | Administration | System Admin | H | Admin or superuser exists | Open system administration dashboard | 1. Log in as admin user; 2. Open system admin route | Administrative dashboard loads and privileged actions are visible | Not Started
UAT-048 | Administration | System Admin | H | Non-admin user exists | Block system admin access for non-admin | 1. Log in as standard user; 2. Attempt to open system admin route | Unauthorized user is denied access or redirected | Not Started
UAT-049 | Administration | System Admin | M | Admin user exists; at least one managed user exists | Update a managed user from admin panel | 1. Open admin dashboard; 2. Change user active state or filter users; 3. Save | Administrative change persists and is reflected in user access state | Not Started
UAT-050 | Academy | Academy Landing | H | Authenticated user exists | Open SME Academy landing page | 1. Log in; 2. Open academy route | Academy page loads with sidebar, content panels, and no missing asset errors | Not Started
UAT-051 | Academy | Courses | H | Academy catalogue is seeded | Browse course catalogue | 1. Open academy; 2. Browse courses or learning paths | Courses, paths, and metadata display correctly | Not Started
UAT-052 | Academy | Enrollment | H | At least one publishable course exists | Enroll in a course | 1. Open a course; 2. Start or enroll; 3. Confirm action | Enrollment is created and visible in learner progress | Not Started
UAT-053 | Academy | Learning Progress | H | Enrolled learner and course modules exist | Complete a course module or lesson step | 1. Open active enrollment; 2. Mark module complete or finish quiz/task | Progress percentage updates and module state persists | Not Started
UAT-054 | Academy | Certificates | M | Course completion criteria met | View generated certificate | 1. Complete required course; 2. Open certificate | Certificate renders correctly and is only accessible to the owning learner | Not Started
UAT-055 | Academy | Resources | M | Academy resources are seeded | View academy resources | 1. Open resources area; 2. Filter or open a resource | Resources list loads and resource details match configured content | Not Started
UAT-056 | Academy | Business Diagnostic | H | Diagnostic content is seeded | Submit business diagnostic | 1. Open diagnostic; 2. Answer all questions; 3. Submit | Diagnostic returns scores or recommendations without validation errors | Not Started
UAT-057 | Academy | Funding & Opportunities | M | Funding data is seeded | Review funding and opportunity content | 1. Open funding section; 2. Filter or review detail items | Funding items display correctly with categories and details | Not Started
UAT-058 | Academy | Events & Webinars | M | Event content is seeded | Register for an academy event | 1. Open events; 2. Register for an event | Registration succeeds once and avoids duplicate registration issues | Not Started
UAT-059 | Academy | Mentorship | M | Mentor and booking data are seeded | Book a mentorship session | 1. Open mentorship; 2. Book available mentor/time | Booking request succeeds and appears in learner session history if supported | Not Started
UAT-060 | Academy | Community | M | Forum categories are seeded | Create a community discussion post | 1. Open community; 2. Create post; 3. Save | Post appears in community feed and can be replied to according to permissions | Not Started
UAT-061 | Academy | Academy Admin | H | Academy admin user exists | Open academy admin management surfaces | 1. Log in as admin; 2. Open academy management screens | Admin management pages load with create/edit capabilities for content | Not Started
UAT-062 | Academy | Funding Import | H | Admin user exists; sample funding CSV exists | Import funding opportunities via admin | 1. Open funding import; 2. Upload CSV; 3. Run import | Import completes with success feedback and imported funding appears in management and learner views | Not Started
UAT-063 | API | Browsable API | M | Authenticated user exists | Open authenticated API explorer | 1. Log in; 2. Open /api/v1/ or /api/ route | Browsable API opens for authenticated session and listed endpoints respond | Not Started
UAT-064 | Security | Protected Routes | H | User is logged out | Prevent anonymous access to protected modules | 1. Log out; 2. Attempt to access protected routes directly | Anonymous user is redirected to login for protected pages | Not Started
UAT-065 | Security | Role Restrictions | H | Multiple roles available | Verify role restrictions across payroll and system admin | 1. Test access with staff, admin, and CEO accounts; 2. Compare route access | Restricted routes are available only to permitted roles and denied for others | Not Started
UAT-066 | Regression | Cross-Module Client-to-Invoice | H | Client, product, sales, and billing modules operational | Create customer flow from client to invoice | 1. Create client; 2. Create sales order; 3. Convert or create invoice; 4. Record payment | End-to-end commercial flow succeeds with consistent customer, totals, and statuses | Not Started
UAT-067 | Regression | Cross-Module Procure-to-Stock | H | Supplier, purchasing, and inventory modules operational | Create procure-to-stock flow | 1. Create supplier; 2. Raise PO; 3. Receive goods; 4. Check inventory | Received goods update stock correctly and PO status reflects receipt | Not Started
UAT-068 | Regression | Cross-Module Expense-to-Finance | H | Expense and finance modules operational | Validate approved expense impact | 1. Submit expense; 2. Approve expense; 3. Review finance overview or reports | Approved expense is visible in operational flow and reflected in financial summaries where expected | Not Started
UAT-069 | Regression | Cross-Module Document Attachments | M | Document and transactional modules operational | Use document management alongside business records | 1. Upload document; 2. Access related operational module; 3. Confirm document availability or linkage behavior | Document library remains stable and stored files are accessible from intended workflows | Not Started
UAT-070 | Regression | Deployment Smoke | H | Staging or production-like environment available | Run smoke test across all major entry points | 1. Log in; 2. Open each major module route once; 3. Watch for UI errors, broken assets, or server failures | All key pages open successfully with no server errors, broken navigation, or missing static assets | Not Started